## Mobile App
S.No | Task/Module | Assigned To | Status
1 | Login | Sasindran | Completed
2 | Forgot password | Sasindran | Completed
3 | Registration | Sasindran | Completed
4 | Home | Sasindran | In Progress
5 | Menu/Navigation | Sasindran | Completed
6 | Settings | Sasindran | In Progress
7 | Popups/Alerts | Sasindran | Completed
8 | Logout | Sasindran | Completed
9 | Theme | Sasindran | Completed
10 | App icons | Sasindran | Completed
11 | Splash Screen | Sasindran | Completed
12 | Details | Sasindran | In Progress

## Web API
S.No | Task | Assigned To | Status

## Database
S.No | Task | Assigned To | Status

## QA
S.No | Task | Assigned To | Status